# BENCH R&D PROGRAM

# RESOURCE LIFECYCLE PLAYBOOK

| Document Owner | Head of Engineering | Applies To | All R&D Projects |
| --- | --- | --- | --- |
| Review Cycle | Quarterly | Version | 1.0 |
| Related Docs | R&D Program Plan · Project Portfolio · Operations Handbook · Templates & Checklists |  |  |

# Purpose

This playbook covers every point at which a person moves into, through, or out of an R&D project. Rotators, tech leads, 20% contributors, BU consumers. Planned transitions and emergency pulls. Project activations and retirements.

It exists because the highest-risk moments in the R&D program are transitions. Bad onboarding wastes the first week of a rotation. Bad offboarding kills the project. Good process here is the difference between a program that compounds and a program that leaks.

Use this doc in the moment. Don't memorize it. When a rotator is joining, open Section 1 and follow the checklist.

# Section 1 — Rotator Onboarding

Triggered when a bench engineer is assigned to an R&D project.

## 1.1 Day 0 (Before Rotation Starts)

Owner: Engineering Manager + Tech Lead

- Engineering Manager confirms rotator assignment in bench tracker

- Engineering Manager notifies Tech Lead with expected start date and estimated bench window

- Tech Lead identifies specific project scope for the rotator (which module, which open questions)

- Tech Lead pre-provisions repo access, Slack channel invite, IDP entry access

- Tech Lead selects one near-term in-demand skill the rotation will target for growth

- Engineering Manager sends rotator the welcome message (template in Templates doc)

## 1.2 Day 1 — Kickoff

Owner: Rotator + Tech Lead

- 30-minute kickoff call between rotator and tech lead

- Tech Lead walks rotator through: project purpose, current state, open questions, chosen contribution scope

- Tech Lead confirms the targeted in-demand skill for this rotation

- Rotator confirms scope understanding

- Rotator gets pointed to: repo, IDP entry, MVH package, knowledge/ directory, past retros

- Rotator joins project Slack channel and introduces themselves

- End of day: rotator has cloned repo and verified local environment runs

## 1.3 Day 2 — First Task

Owner: Rotator

- Rotator picks first task from the project backlog (or accepts one assigned by tech lead)

- Rotator opens EPAV /evaluate on the task

- Rotator posts first progress note in project Slack channel

- End of day: at least one commit or documented investigation

## 1.4 Day 5 — First Week Check-In

Owner: Rotator + Tech Lead

- 15-minute check-in call

- Rotator demos progress or discusses blockers

- Tech Lead reviews rotator's MVH package baseline (should exist by end of week 1)

- Confirm rotator is on track for their first shippable contribution

- Adjust scope if week 1 revealed the task is too large or too small

## 1.5 Rotator Onboarding Complete When

- Rotator has environment working

- Rotator has first task in progress via EPAV

- MVH package baseline created

- Weekly check-in cadence established

- Rotator knows which in-demand skill they're growing

# Section 2 — Rotator Active Period

The steady state during a rotation.

## 2.1 Weekly Rhythm for a Rotator

| Day | Activity |
| --- | --- |
| Monday | Attend bench standup (15 min); confirm this week's target with tech lead |
| Tuesday–Thursday | Execute EPAV cycles; commit progress; update task status |
| Friday | Update MVH package; post weekly progress note; flag any pull-to-client risk |

## 2.2 Progress Tracking

- All work is tracked in the project's task management (whatever the org uses)

- Rotator updates task status daily

- MVH package updated weekly (Fridays) at minimum

- Any blocker open more than 24 hours is flagged in Slack

## 2.3 Contribution Flow

- Rotator completes task via EPAV

- /validate passes

- Pull request opened

- Tech lead reviews (target: 24-hour review turnaround)

- Rotator addresses review comments

- Tech lead merges

- Rotator posts completion note in project Slack

## 2.4 Blocker Escalation

| Blocker Duration | Escalation |
| --- | --- |
| < 24 hours | Rotator posts in project Slack; tech lead assists |
| 24–48 hours | Tech lead escalates to Engineering Manager |
| > 48 hours | Engineering Manager escalates to Head of Engineering; possible task reassignment |
| > 5 days | Task is unblockable at project level; consider project pause or re-scope |

# Section 3 — Rotator Offboarding (Planned)

Triggered when the rotator's bench window is ending with at least 3 days notice.

## 3.1 Day -3 (3 Days Before Rotation Ends)

Owner: Rotator + Tech Lead

- Rotator confirms rotation end date to tech lead

- Tech Lead decides: is this rotator's work finishing, or handing off to another rotator?

- If handing off: identify incoming rotator (or mark project for future pickup)

- Rotator begins wind-down; no new tasks started

## 3.2 Day -2

Owner: Rotator

- Rotator completes final in-progress task or brings to a clean pause point

- MVH package fully updated

- Any open PRs merged or clearly labeled "in progress"

## 3.3 Day -1

Owner: Rotator + Tech Lead

- Rotator creates or updates the Resumption Document (template in Templates doc)

- Rotator writes retro entry in knowledge/retros/ covering: what shipped, what was learned, what's next, any gotchas

- Skill growth captured in capability tracker (which in-demand skill grew and how)

- 15-minute exit review with tech lead

## 3.4 Day 0 — Last Day

Owner: Rotator

- Post final update in project Slack acknowledging contribution

- Confirm handoff email/message sent to incoming rotator (if applicable)

- Get recognition at next show-and-tell scheduled

## 3.5 Planned Offboarding Complete When

- MVH package current

- Retro entry written

- Resumption document current

- Skill growth logged

- Incoming rotator identified (or project state marked "paused, ready for pickup")

# Section 4 — Rotator Offboarding (Unplanned Pull)

Triggered when a rotator is pulled to client work with less than 3 days notice — the more common scenario in outsourcing.

## 4.1 Emergency Handoff Protocol (< 24 hour notice)

Owner: Rotator + Tech Lead

Within 4 hours of notification:

- Rotator notifies tech lead immediately

- Tech lead assesses: what state is the work in?

- Rotator stops in-progress task at nearest clean boundary (commit early, commit often)

Within 24 hours (before rotator's last day on R&D):

- Rotator commits and pushes all work-in-progress with clear commit messages ("WIP: [task] — [state]")

- Rotator updates MVH package with current state (even if incomplete)

- Rotator writes short Resumption Document — bullet points only, minimum viable

- Rotator writes quick retro entry in knowledge/retros/ — what was tried, what worked, what to avoid

- Rotator posts final note in project Slack with @tech-lead tagged

- Tech lead confirms receipt of handoff artifacts

## 4.2 Unplanned Offboarding Minimum Viable Handoff (MVH)

Even in a crisis pull, these are non-negotiable:

- Current code committed and pushed

- One-paragraph note on "what state is this in"

- Contact info if any question arises (rotator is willing to answer 1-2 questions post-pull)

Anything beyond that is a bonus. The above is the floor.

## 4.3 Post-Pull: Tech Lead Actions

Within 48 hours of rotator's pull:

- Tech lead reviews handoff artifacts

- Tech lead decides: pick up the work themselves, reassign to another rotator, or pause the specific task

- Tech lead updates project state in IDP if project is now short-staffed

- If project is now unstaffed: mark project as Paused, create Resumption Doc

## 4.4 If No Handoff Was Possible

Sometimes the pull is so fast the rotator can't do handoff. In that case:

- Tech lead runs git log to reconstruct rotator's last work

- Tech lead writes the Resumption Doc themselves based on commits

- Note in knowledge/retros/ that handoff was impossible — improvement item for the next rotator onboarding (add earlier MVH updates)

# Section 5 — Tech Lead Onboarding

Triggered when a new tech lead takes on an R&D project (new project, or replacing previous tech lead).

## 5.1 Tech Lead Selection Criteria

- Senior engineer (3+ years relevant experience)

- Currently on client work at ≤80% allocation OR post-bench transitioning back to client

- Interested in the project domain

- Comfortable reviewing others' work daily

- Willing to commit 10–20% time (formal allocation, not "when free")

## 5.2 First-Week Onboarding for New Tech Lead

Owner: Head of Engineering + Previous Tech Lead (if replacement)

### Day 1

- Head of Engineering briefs new tech lead on project purpose, current state, portfolio context

- Formal time allocation documented (e.g., "20% Fridays + 1 hour daily") and communicated to their client team

- Access provisioned: repo admin, IDP admin for the project, project Slack ownership

### Day 2–3

- Deep-dive with previous tech lead (if replacement): architecture walkthrough, open questions, current rotators, known issues

- Read the Resumption Doc, MVH package, and recent knowledge/retros/ entries

- Meet each active rotator 1:1 (15 min each)

- Meet the BU stakeholder(s) consuming the project's output

### Day 4–5

- Attend weekly bench standup as project representative

- Post introduction in project Slack

- Do first tech lead review of an active PR

- Confirm rotator assignments for the coming 2 weeks

## 5.3 Tech Lead Onboarding Complete When

- Time allocation formalized

- Rotator 1:1s done

- First PR review completed

- BU stakeholders identified and met

- Coaching cadence set with Head of Engineering (biweekly for first 2 months)

# Section 6 — Tech Lead Transitions

Triggered when a tech lead needs to step down or hand off.

## 6.1 Common Triggers

- Client engagement pulling their full time

- Personal circumstances

- Better tech lead candidate available

- Project transitioning to a new phase requiring different expertise

## 6.2 Transition Protocol

Ideal case (2+ weeks notice):

- Outgoing tech lead notifies Head of Engineering

- Head of Engineering identifies replacement candidate

- Overlap period: 2 weeks of joint operation

- Outgoing tech lead runs Section 5 onboarding for incoming

- Formal handoff at end of overlap (project state, key decisions pending, rotator status, stakeholder relationships)

Short-notice case (< 1 week):

- Outgoing tech lead updates all project artifacts (MVH, Resumption Doc, tech decision log)

- Head of Engineering steps in as interim tech lead

- Head of Engineering runs replacement selection over 2–4 weeks

- New tech lead onboards per Section 5 with Head of Engineering as previous-lead proxy

Crisis case (immediate):

- Project marked Paused immediately

- Head of Engineering owns Resumption Doc creation

- Project resumes when new tech lead is assigned (may be weeks later)

- Accept that scope may need refresh before resumption

# Section 7 — 20% Contributor Onboarding

Triggered when a non-bench engineer wants to contribute part-time to an R&D project.

## 7.1 Eligibility

- Engineer's current client work must have capacity for 4–8 hours/week of R&D time

- Engineer's manager approves the time commitment

- Engineer picks ONE track (not multiple — prevents scattering)

- Engineer commits to at least 8 weeks of engagement (below that, ramp-up cost exceeds contribution)

## 7.2 Onboarding Flow

### Week 1

- Engineer expresses interest to their Engineering Manager

- Engineering Manager confirms client-work capacity, approves the time

- Engineer picks track and contacts that track's tech lead

- Tech Lead confirms suitability and available contribution scope

- Engineer added to project Slack, given repo access

### Week 2

- Engineer completes lightweight version of Section 1 onboarding (Day 0, Day 1 kickoff, environment setup)

- Engineer picks first small contribution (aim for 2–3 week completion)

- First contribution shipped or shown to tech lead

## 7.3 20% Contributor Weekly Rhythm

- No mandatory standup attendance (they have client standups)

- Post weekly progress update in project Slack (Fridays)

- Tech lead reviews contributions in normal PR flow

- No MVH package requirement (contributions are self-contained enough)

## 7.4 20% Contributor Offboarding

Simpler than rotator offboarding:

- Complete current contribution or hand off partial work with commit + note

- Post departure note in project Slack

- Contribution added to capability tracker

# Section 8 — Project Activation

Triggered when a new R&D project is being added to the portfolio.

## 8.1 Pre-Activation Checklist

Before a project can activate:

- Project fits capacity-elastic model (Anchor / Tier 1 Parallel / Tier 2 Future)

- Tech lead identified and committed

- BU consumer identified and committed to using output

- v1 scope defined (one-page spec)

- At least 2 near-term in-demand skills coverage confirmed

- Rotator capacity available (per capacity table in Program Plan)

- Fits within active portfolio without displacing higher-priority projects

## 8.2 Activation Flow

Week 1 of new project:

- Project registered as component in Backstage IDP with owner, tech lead, description

- Repo created and scaffolded via toolkit initialization + /scaffold

- knowledge/ directory initialized with project-specific rules and patterns

- Initial task backlog created (EPAV task CSV)

- Project Slack channel created and populated

- Tech Lead onboarded per Section 5

- First rotators identified for Week 2 start

Week 2:

- First rotators onboarded per Section 1

- First EPAV cycles running

- Weekly cadence established

## 8.3 Activation Complete When

- Project state is Active in IDP

- Tech lead running weekly standups

- MVH packages being maintained

- First contribution merged (target: end of Week 3)

# Section 9 — Project Pause and Dormancy

Triggered when a project loses all active rotators (usually due to bench shrinkage).

## 9.1 Pause Protocol

When last rotator is being pulled:

- Rotator completes offboarding per Section 3 or 4

- Tech Lead reviews handoff artifacts, ensures Resumption Doc is current

- Tech Lead updates project state in IDP: Active → Paused

- Tech Lead posts pause notice in project Slack (channel stays open)

- Project remains in portfolio, ready to resume

## 9.2 During Pause

- Tech lead maintains project (light touch — no code work, but keeps IDP entry current)

- Resumption Doc remains accessible

- Any inbound BU questions handled by tech lead

- No new work until resumption

## 9.3 Dormancy (60+ Days Paused)

- Tech lead reviews project for scope refresh

- May propose scope changes based on tech evolution

- Update Resumption Doc with refreshed context

- Project state remains Paused until resumption triggers

## 9.4 Resumption Protocol

Triggered when rotator capacity becomes available:

- Head of Engineering + Tech Lead confirm project is next priority

- Tech Lead does scope refresh if dormant > 60 days

- New rotator picks up per Section 1 onboarding + reads Resumption Doc

- Project state updated: Paused → Active

- Resumption noted in knowledge/retros/

# Section 10 — Project Retirement

Triggered when a project is complete, abandoned, or superseded.

## 10.1 Retirement Reasons

- Complete: v-final shipped, feature-complete, in production, no further R&D needed (moves to maintenance)

- Superseded: newer approach makes this project obsolete

- Abandoned: project failed to produce value, or scope proved wrong

## 10.2 Retirement Protocol

- Head of Engineering approves retirement decision

- Final retro written in knowledge/retros/ covering: what was learned, why retiring, what to preserve

- Any reusable assets extracted and contributed to shared toolkit catalog

- If Complete: project handed to maintenance owner (BU team, product team, etc.)

- If Abandoned: honest post-mortem — what would we do differently

- Project state updated: → Retired

- Slack channel archived (not deleted; searchable history preserved)

# Section 11 — BU Consumer Onboarding

Triggered when a new BU wants to consume output from an existing R&D project.

## 11.1 Onboarding Flow

- BU head contacts Head of Engineering or project tech lead

- Requirements gathered: what output does the BU need, how often, in what format

- Tech lead confirms scope fits existing project or requires new module

- If new module: added to project's next-milestone planning

- BU stakeholder invited to project Slack channel

- Delivery mechanism configured (email list, chat channel, etc.)

- First delivery scheduled

## 11.2 BU Feedback Loop

- BU head is expected to give feedback within 2 weeks of first delivery

- Ongoing feedback captured in project Slack or in a shared doc

- Major feedback drives next-milestone scope

- BU is a stakeholder for show-and-tells

# Appendix A — Quick Reference Card

Print this and pin it somewhere visible.

When a rotator is joining: Section 1 When a rotator is leaving (planned): Section 3 When a rotator is being pulled unexpectedly: Section 4 When a new tech lead is starting: Section 5 When a tech lead is stepping down: Section 6 When a 20% contributor wants in: Section 7 When a new project is starting: Section 8 When a project needs to pause: Section 9 When a project is done: Section 10 When a new BU wants output: Section 11

## Non-Negotiables (Do NOT skip, regardless of speed)

- MVH package before any rotator exit — even 4 bullet points is better than nothing

- Resumption Doc before project pause — the project can wait; the context can't be recovered later

- Tech lead formal time allocation — "when they have time" fails; documented percentage succeeds

- BU commitment before project activation — no committed consumer means no real project

- Skill growth logged per rotation — the whole program is measured on this; don't skip capture